## timetable
| 1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
ANNEX 3: WORK PLAN revised | Legend: |  |  | initially planned |  |  |  | Revisions proposed by the First Progress Report | [6 empty] | Revisions proposed by the Second Progress Report | [6 empty] | Revisions proposed by the 3 Progress Report
PROJECT IMPLEMENTATION PERIOD (24 months)
| Sep 2019 | Oct 2019 | Nov 2019 |  | Dec 2019 | Jan 2020 | Feb 2020 | Mar 2020 | Apr 2020 | May 2020 | Jun 2020 | Jul 2020 | Aug 2020 | Sep 2020 |  | Oct 2020 | Nov 2020 | Dec 2020 | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021
Inception Phase
0.1. Kick-off Meeting with the Contracting Authority
0.2. Setting up of the Project office
0.3. Orientation meetings with beneficiaries and analysis of background documents
0.4. Support in establishment of the Project Steering Committee
0.5. Developing the work plan
0.6. Drafting and submission of the Inception Report
Component 1: Development of key policy and framework documents
1.1. Development of the national key competence curriculum framework
1.2. Development of the implementation and monitoring plans for STEM setting out timelines and assigning responsibilities and functions to key actors, on the basis of the developed national competence framework;
1.3. Development of quality assurance standards for STEM to be integrated within national QA processes;
Component 2: Curriculum development - Development and review of education programmes, guidelines and assessment criteria
2.1. Revision of science, maths, engineering and technology primary and secondary school curriculum, resources and teaching methods and competences;
2.2. Revision of CPD and initial teacher education in STEM from the point of view of key competences;
2.3. Organise customised study-visit to appropriate EU member state for policy makers to explore and verify proposals for curricula, teaching, learning and assessment methodologies
2.4. Development of teacher guidelines for teachers teaching STEM;
2.5. Development of methodological instructions and guidelines for assessment criteria and their linking with education outcomes through formative assessment;
2.6. Pilot revision of mathematics study programme with regards to pedagogy and psychology, didactic and methodology aspects and content, with focus on innovative teaching pedagogy and STEM competences;
Component 3: Teacher training (pre-service and CPD) for delivering key competences and STEM
3.1. Development of teacher training programmes on key competences on the basis of the new key competence strategic framework, with particular focus on STEM;
3.2. Delivering teacher training programme on key competences for 960 STEM teachers (32 two-day seminars);
3.3. Delivering teacher training for 900 ISCED 1 level primary school teachers for key competences (30 two-day seminars);
3.4. Support the trainings, develop and regularly maintain on-line platform to support teacher training and peer learning through exchange of practice
Component 4: Quality assurance
4.1. Development and introduction of key competence indicators in QA methodology and revision, and improvement of appropriate criteria and processes for internal and external evaluation;
4.2. Consultations (training) of members of school internal evaluation team for internal evaluation in primary and secondary schools (12 one-day seminars, for approximately 360 persons);
4.3. Training and support to staff in the BES, the schools and HE institutions that are directly responsible for quality assurance (including internal and external evaluation) with respect to STEM (3 two-day seminars for approximately 30 persons);
Component 5: Analysis of inputs, processes and outputs of STEM
5.1. Carrying out national research for II and III cycles (ISCED 1 and ISCED 2 levels) for STEM disciplines (using representative sample) (develop a study);
5.2. Developing the new assessment items for testing student achievements in STEM disciplines.
5.3. All activities under components should be coordinated with respect to timing and results.
Cross-cutting activities
6.1. Project monitoring and evaluation
6.2. Meetings of the PSC
6.3. Reporting the Project progress
Project Closure
7.1. Conducting the hand-over process and closing the Project office